CHANAKYA PM

How the Tool Works

A plain-language guide for site teams, planning teams, and management

Version 35  ·  April 2026  ·  Internal use only

# 1.  What is Chanakya PM?

Chanakya PM is the Amanvana project's internal tracking tool. It lets site teams log work progress, planning teams see how every villa is doing, and management get a live status at a glance — all in one screen, with no paper forms or spreadsheets to update separately.

Everything is stored in your browser. No internet connection is needed once the file is open. No data goes to a server.

⚠ Important Because data is stored in the browser, do not clear your browser history or browser data without taking an export first. Each device has its own copy — updates made on one computer do not automatically appear on another.

# 2.  How Work is Organised (Three Levels)

Every piece of work in the tool sits at one of three levels. Think of it like folders inside folders:

| Level | What it represents | Example |
| --- | --- | --- |
| Phase | A major stage of construction for one villa | Foundation Work |
| Task | A specific activity within a phase | Column Casting |
| Subtask | The individual work item you update progress on | RCC Columns — Ground Floor |

✓ How it works A villa is a project. Each project has its own set of Phases, Tasks, and Subtasks. Progress rolls up automatically — update a Subtask and the Task, Phase, and Villa all update.

# 3.  How Progress is Calculated

## 3.1  Subtask progress

Each subtask has a progress percentage (0% to 100%) that you enter manually or change by clicking its status button.

✓ How it works Updating status also updates progress: • Not Started → 0% • In Progress → keeps whatever % you entered • Completed → 100% (automatic)

## 3.2  Task and phase progress (duration-weighted)

The progress shown for a Task or Phase is not a simple average. It is a weighted average based on how many days each subtask is scheduled to take. This means a task that takes 10 days counts more than one that takes 2 days — which gives you a more accurate picture.

ℹ Note Example: A phase has two subtasks. Subtask A: 10 days long, 80% done Subtask B: 2 days long, 0% done Simple average would show 40%. Duration-weighted shows 67% — because Subtask A is the bigger piece of work.

## 3.3  Villa-level progress

The overall progress percentage shown on a villa card on the dashboard is the same duration-weighted calculation applied across all subtasks in that villa. It gives a single, honest number for how far along the villa is.

# 4.  Villa Status — How It Is Set

The tool automatically works out a villa's status every time you save a task update. It does not need to be set manually. Here is the logic it uses, in order:

| Status shown | What it means | When this is set |
| --- | --- | --- |
| Not Started | No work has begun on any task | All tasks are at 0% |
| On Track | Work is active, no problems detected | Some tasks started; no blocked or overdue tasks |
| At Risk | There is a problem that needs attention | One or more tasks are blocked OR overdue (past their planned finish date and not yet done) |
| Completed | All work is done | Every task is at 100% or marked Completed |
| Delayed | Manually flagged by management | Set manually via Edit Project — for management override |

✓ How it works The tool checks for blocked tasks and overdue tasks every time a save happens. A task is overdue if its planned finish date has passed and it is not yet completed. You do not need to manually set 'At Risk' — the tool does it for you.

# 5.  Dates — Planned vs. Actual

The tool tracks two sets of dates for each task:

| Date type | What it means | Who sets it |
| --- | --- | --- |
| Planned Start | When the task was originally scheduled to begin | Set when task is created |
| Planned Finish | When the task was originally scheduled to end | Set when task is created |
| Actual Start | The real date work began on site | Auto-set when status changes to In Progress; can also be entered manually |
| Actual Finish | The real date the task was completed | Auto-set when status changes to Completed; can also be entered manually |

⚠ Important Actual dates can only be set to today or within the last 14 days. You cannot enter future dates as actuals. Planned dates stay unchanged once the task is created — they form the baseline schedule.

## 5.1  Projected End Date

On the villa detail panel, a 'Projected End' date is shown. This is worked out as:

- For tasks already completed: the date they actually finished (Actual Finish)

- For tasks still in progress: their planned finish date

This gives the most realistic estimate of when the villa will be done — based on real completion dates where available.

# 6.  Changing Task Status — The Status Button

Each task in the Work Breakdown (WBS) view has a status button you can click to move the task forward. It cycles through three states:

| Click action | Status changes to | What else happens |
| --- | --- | --- |
| First click | In Progress | Actual Start date is stamped with today |
| Second click | Completed | Actual Finish date is stamped with today; progress set to 100% |
| Third click | Not Started (reset) | Actual Finish is cleared; progress set back to 0% |

ℹ Note If a task is Blocked or On Hold, the cycle button does not apply. Those statuses must be changed manually through Edit Task.

# 7.  Notes

Every task can carry notes — useful for logging site observations, blockers, instructions, or handover messages. Key things to know:

- Notes are permanent. Once added, a note cannot be deleted or changed.

- Each note shows who added it and when.

- Notes are visible to anyone who opens the task in Edit mode.

- There is no limit to the number of notes on a task.

✓ How it works Use notes to record why a task was delayed, what the site condition was, or any instruction given on-site. Because notes cannot be edited, they form a reliable record of what happened and when.

# 8.  The Dashboard — What Each Number Means

The dashboard is the first screen you see. It shows a summary of all villas and key counts at the top.

| Card | What it counts |
| --- | --- |
| Total Villas | How many villa projects exist in the system |
| Baseline Fixed | Number of villas with a confirmed schedule baseline (currently tracked manually) |
| Active | Villas where work has started and is not yet complete — includes On Track, At Risk, and Delayed |
| On Track | Active villas with no blocked or overdue tasks |
| At Risk | Active villas that have at least one blocked task, or one task past its planned finish date |
| Completed | Villas where all tasks are 100% done |

✓ How it works All these numbers update automatically when you save a task. There is nothing to manually refresh. Click any card to filter the villa grid below to show only matching villas.

## 8.1  Alert Strip

Below the summary cards is the alert strip. It shows one type of alert:

- Villas with blocked tasks — lists how many villas have at least one task in Blocked status. Click it to filter the grid.

If there are no alerts, it shows 'No active alerts'.

# 9.  Adding and Editing Tasks

## 9.1  Adding a new task

When you click 'Add Task', a panel opens with the following fields:

| Field | What to enter |
| --- | --- |
| Task Name | A short, clear name for the work item |
| Phase | Select which phase this task belongs to |
| Subphase / Task Group | The activity group within the phase |
| Status | Start as Not Started unless work is already underway |
| Priority | Low / Medium / High — used to highlight urgent items |
| Progress % | How far along the task is (0–100) |
| Assigned To | Team member responsible |
| Planned Start & Finish | The scheduled dates for this task |
| Actual Start & Finish (optional) | Enter only if work has already begun or finished — must be today or within the last 14 days |
| Duration (days) | Auto-calculated from the planned dates |
| Notes | Any additional context you want to log immediately |

## 9.2  Editing an existing task

Click the edit icon on any task row. The panel opens showing the current values. In Edit mode, the date fields show Actual Start and Actual Finish (not planned dates). Update these to reflect what happened on site.

✓ How it works Planned dates (the original schedule) are never overwritten when you edit a task. Only actual dates change in Edit mode, preserving the baseline schedule for comparison.

# 10.  The WBS (Work Breakdown) View

The WBS tab shows all tasks for the selected villa in a structured table. Tasks are grouped by Phase, then by Subphase.

| Row type | What you see in the Name column | What you see in the Progress column |
| --- | --- | --- |
| Phase row | Phase name | Overall % complete for that phase (duration-weighted) |
| Subphase row | Subphase name + 'X out of Y done' | % complete for that subphase (duration-weighted) |
| Task row | Individual task name | That task's own progress percentage |

You can collapse or expand phases and subphases by clicking the row header. The Collapse All and Expand All buttons at the top control everything at once.

# 11.  Filters and Search

On the dashboard, you can filter the villa grid by:

- Search text — any part of the villa name or zone

- Status — show only On Track, At Risk, Completed, etc.

- Zone — filter by the development zone (e.g. Zone A)

- Contractor — filter by the contractor assigned to the villa

Click any stat card to apply a status filter automatically. Use 'Clear Filters' to reset to all villas.

# 12.  Resources (Team Members)

The Resources section lets you define team members — site supervisors, contractors, subcontractors — and attach them to tasks as the assigned person.

- Each resource has a name, role, email, phone, and availability (%).

- Resources are assigned to tasks via the 'Assigned To' field.

- The Resource view shows all resources and what they are assigned to.

ℹ Note Resource assignment is for reference only — the tool does not check workload or flag conflicts. Use the Assigned To field to make clear who is responsible for each task.

# 13.  Schedule Baseline

A baseline is a snapshot of the planned schedule taken at a specific point in time — usually when the plan is approved and work is about to begin. Once set, the baseline is frozen and does not change even if tasks are updated later.

The Baseline view lets you compare the current plan against the frozen baseline to see where dates or progress have shifted.

⚠ Important Only one baseline can be stored at a time. If you set a new baseline, the old one is replaced. Setting a baseline is a team lead action — it should be done when the plan is approved, not during daily updates.

# 14.  Known Limitations

Chanakya PM is currently built as a single browser-based file. Some things it cannot do yet that a full production system would support:

| Limitation | What this means for your team |
| --- | --- |
| No shared server | Updates made on one computer do not sync to another — each device has its own copy |
| No login / user accounts | Anyone who has the file can make changes — there is no individual login |
| No automatic backup | If browser data is cleared, all data is lost — export your data regularly |
| One baseline only | You cannot store multiple historical baselines for comparison |
| No capacity planning | The tool shows who is assigned to tasks but does not flag overloaded team members |

ℹ Note These limitations are known and planned to be addressed when the tool moves to a production server with a database and user accounts.

# 15.  Glossary

| Term | Plain-language meaning |
| --- | --- |
| WBS | Work Breakdown Structure — the task list view, organised by Phase and Subphase |
| Baseline | A frozen copy of the original planned schedule, used for comparison later |
| At Risk | A villa where something needs attention — blocked tasks or missed planned dates |
| Blocked | A task that cannot progress because of an external dependency or issue |
| Duration | The number of days a task is scheduled to take (Planned Finish minus Planned Start) |
| Duration-weighted progress | A smarter average that gives more weight to longer tasks — so a 10-day task counts more than a 1-day task |
| Actual Start / Finish | The real dates work began and ended, as opposed to the planned (scheduled) dates |
| Projected End | The estimated date the villa will be fully complete, based on actuals plus remaining planned dates |
| Milestone | A task marked as a key checkpoint — shown with a diamond icon in the WBS |
| Predecessor | A task that must finish (or start) before another task can begin |
| Status cycle | Clicking the status button to move a task through Not Started → In Progress → Completed |

Chanakya PM

This document is for internal use by the Amanvana project team.

Questions? Contact the Planning Team.