Chanakya PM

System Logic & Architecture Reference

Version: v35  |  Last Updated: April 2026  |  Internal Use Only

# 1. Overview

Chanakya PM is a single-file HTML construction project management tool. All state is stored in the browser's localStorage. There is no server-side backend — all logic runs in the browser. The tool manages villa-level projects with a three-level task hierarchy, supports multiple team members, and tracks progress, dates, notes, and blockers.

## 1.1 File Structure

- Single monolithic HTML file (~12,000+ lines)

- All JavaScript, CSS, and HTML in one file — no build system, no external dependencies

- localStorage is the sole persistence layer

- All rendering functions run client-side in real time

# 2. Data Architecture

## 2.1 localStorage Keys

| Key | Contents | Notes |
| --- | --- | --- |
| _cky_tasks | Task data for all projects | Primary task store. Keyed by project ID. |
| _cky_planner | Planner task view store | Unified with _cky_tasks via DB.sTasks() |
| _ckdat3 | Project (villa) definitions | Name, zone, type, status, planned dates |
| _cky_bl | Baseline snapshot data | Frozen copy of tasks for schedule baseline |
| _cky_res | Resource definitions | People, roles, rates, availability |

## 2.2 DB Layer

All reads and writes go through a DB abstraction layer to centralise localStorage access:

DB.tasks()        → read all tasks (merged _cky_tasks + _cky_planner)

DB.projs()        → read all project definitions from _ckdat3

DB.sTasks(data)   → write task data to both stores

DB.sProjs(data)   → write project data to _ckdat3

DB.res()          → read resources from _cky_res

DB.sRes(data)     → write resources

DB.save()         → flush all state to localStorage

⚠ Note DB.save() is called inside syncProjStatus() which itself is called from saveTask(). This can cause a double-save. It's harmless in practice but should be reviewed if performance becomes a concern.

## 2.3 State Object (S)

A global state object S holds runtime state for the current session:

S.proj       → currently selected project object

S.coll       → collapse state map for WBS (keys: ph_<phaseId>, sp_<subphaseId>)

S._gq/_gs/_gz/_gc  → dashboard filter values (query, status, zone, contractor)

# 3. Project Hierarchy

## 3.1 Three-Level Structure

Every task belongs to three levels of grouping. The hierarchy is embedded in the task object itself — there are no separate phase/subphase objects stored independently.

| Level | Field on Task | UI Label | Purpose |
| --- | --- | --- | --- |
| 1 — Phase | phaseId / phaseName | Phase | Top-level grouping (e.g. Foundation, Structure) |
| 2 — Subphase | subphaseId / subphaseName | Task | Mid-level grouping (e.g. Earthwork, Columns) |
| 3 — Task | id / name | Subtask | Individual work item with progress, dates, assignee |

ℹ Info A task whose subphaseName equals its phaseName is treated as a direct child of the phase — the subphase header is not shown as a duplicate in the WBS view. This is handled by the isSameAsPhase check in renderWBS().

## 3.2 Task Object Schema

Each task object stored in _realTasks[pid] contains:

| Field | Type | Description |
| --- | --- | --- |
| id | string | Unique ID, format: <pid>-T<timestamp> |
| name | string | Task display name |
| phaseId / phaseName | string | Phase grouping |
| subphaseId / subphaseName | string | Subphase grouping |
| status | enum | not-started ¦ in-progress ¦ completed ¦ blocked ¦ on-hold |
| progress | number 0–100 | Percentage complete |
| duration | number | Duration in days (used as weight for progress calculation) |
| startDate / endDate | date string | Planned start and finish dates |
| actualStartDate | date string | Date task was first moved to in-progress |
| actualEndDate | date string | Date task was marked completed |
| assignee | string | Team member name or ID |
| predecessors | array | List of {id, type} dependency links |
| notes | array ¦ string | Append-only notes log |
| cost | number | Estimated cost |
| milestone | 0¦1 | Whether this task is a milestone |
| constraint | string | Scheduling constraint (asap, fnlt, msof, etc.) |
| priority | string | low ¦ medium ¦ high |

# 4. Progress Calculation

## 4.1 Individual Task Progress

Each task carries its own progress value (0–100). Progress can be edited directly or derived from status:

- Status → progress: Completed sets progress = 100. Not-started sets progress = 0.

- Progress → status: 100 sets Completed, 0 sets Not-started, 1–99 sets In-progress.

- Both fields stay in sync via syncStatusToProgress() and syncProgressToStatus().

## 4.2 Subphase / Phase Progress (Duration-Weighted)

Progress at the subphase and phase level is computed using the _wPct() helper which applies duration weighting so longer tasks count proportionally more:

function _wPct(tasks) {

let wSum = 0, wTot = 0;

tasks.forEach(t => {

const w = t.duration || 1;   // use 1 if no duration set

wTot += w;

wSum += Math.min(100, t.progress || 0) * w;

});

return wTot ? Math.round(wSum / wTot) : 0;

}

✓ Correct behavior If a task has no duration set, it defaults to weight = 1 (equal contribution). This prevents division-by-zero and ensures all tasks contribute, even those without duration data.

## 4.3 Villa-Level Progress

The overall progress for a villa is computed from all its tasks using _wPct(allTasks). This single duration-weighted average rolls up the entire task list, regardless of phase or subphase grouping.

## 4.4 WBS Display Rules

| Row Type | Name Cell Shows | Progress Cell Shows |
| --- | --- | --- |
| Phase header | Phase name | Duration-weighted % of all tasks in phase |
| Subphase header | Subphase name + X/Y done | Duration-weighted % of tasks in subphase |
| Task row | Task name | Task's own progress % |

# 5. Villa Status (syncProjStatus)

## 5.1 Status Derivation Logic

syncProjStatus(pid) is called after every task save. It reads all tasks for the villa and derives a status:

| Condition (evaluated in order) | Villa Status Set To |
| --- | --- |
| All tasks completed or progress = 100 | completed |
| No tasks started (progress = 0, status = not-started) | not-started |
| Any task has status = blocked, OR any task has endDate < today and not completed | at-risk |
| Otherwise (some tasks in progress, no blockers/overdue) | on-track |

✓ Correct behavior Previous version only derived 3 statuses: completed / in-progress / not-started. The dashboard 'On Track' and 'At Risk' counters were always 0. Current version correctly derives on-track and at-risk, enabling the dashboard to show real counts.

## 5.2 Status Values Reference

| Status | Meaning | Set By |
| --- | --- | --- |
| not-started | No tasks begun | syncProjStatus (auto) |
| on-track | Active, no blockers or overdue tasks | syncProjStatus (auto) |
| at-risk | Has blocked tasks OR overdue tasks | syncProjStatus (auto) |
| in-progress | Legacy value — still exists in older data | Kept for backward compat |
| completed | All tasks at 100% | syncProjStatus (auto) |
| delayed | Manual override for management visibility | Edit Project modal (manual) |

# 6. Dashboard Metrics (renderStats)

## 6.1 Stat Cards

| Card | Value Source | Notes |
| --- | --- | --- |
| Total Villas | villas.length (dynamic) | Counts all non-infra projects matching active dev filter |
| Baseline Fixed | Hardcoded: 32 | Static — update manually when baselines are confirmed |
| Active | villas with status in-progress ¦ on-track ¦ at-risk ¦ delayed | Dynamic; counts all non-completed, non-idle villas |
| On Track | villas with status = on-track | Dynamic via syncProjStatus |
| At Risk | villas with status = at-risk | Dynamic via syncProjStatus |
| Completed | villas with status = completed | Dynamic via syncProjStatus |

## 6.2 Alert Strip

The alert strip below the stat cards shows real-time operational alerts:

- Villas with blocked tasks: counts unique villa IDs that have at least one task with status = blocked

- No active alerts: shown when no alerts exist

Overdue task alerts were removed in v26 to reduce noise. The alert strip checks blocked tasks only.

## 6.3 Dev Filter

_origDevFilter is a global variable that filters all dashboard views by development/zone. When set, renderStats(), renderGrid(), and related functions only show projects matching that dev value. It is applied consistently across all render functions.

# 7. Date Handling

## 7.1 Date Types

| Field | Meaning | Set When |
| --- | --- | --- |
| startDate | Planned start date | Entered in Add Task modal (Planned Start field) |
| endDate | Planned finish date | Entered in Add Task modal (Planned Finish field) |
| actualStartDate | Actual date work began | Auto-stamped when task moves to in-progress; or entered manually |
| actualEndDate | Actual date work finished | Auto-stamped when task moves to completed; or entered manually |

## 7.2 Add Task Modal — Date Fields

- Planned Start / Planned Finish: free date inputs; set the schedule baseline

- Actual Start / Actual End (optional): restricted to today or earlier (max = today, min = today minus 14 days); stored on creation if provided

## 7.3 Edit Task Modal — Date Fields

Edit Task shows Actual Start and Actual End only (no separate planned date fields). The values saved go directly into actualStartDate and actualEndDate. The planned startDate and endDate from creation are preserved and not overwritten on edit.

## 7.4 Auto Date Stamping (cycSt)

When a user clicks the status cycle button (cycSt) on a task row:

- Not-started → In-progress: actualStartDate stamped with today's date

- In-progress → Completed: actualEndDate stamped with today's date; progress set to 100

- Completed → Not-started: actualEndDate cleared; progress set to 0

## 7.5 Projected End Date

Calculated in renderDetStats() as the latest effective completion date across all tasks:

- Completed tasks: use actualEndDate (or endDate as fallback) — the real date they finished

- Incomplete tasks: use endDate (planned finish) — may be in the past if overdue

This gives the most realistic end estimate: completed work anchored to actual dates, remaining work anchored to planned dates.

# 8. Task Status Cycle (cycSt)

The cycSt(id) function provides a 3-state cycle button on each WBS task row:

| Current Status | Clicked → New Status | Side Effects |
| --- | --- | --- |
| not-started | in-progress | actualStartDate = today |
| in-progress | completed | actualEndDate = today, progress = 100 |
| completed | not-started | actualEndDate = '', progress = 0 |
| blocked | (no cycle — manual edit only) | Status must be changed via Edit Task |
| on-hold | (no cycle — manual edit only) | Status must be changed via Edit Task |

✓ Correct behavior After cycSt changes a task, syncProjStatus() is called automatically to re-derive the villa status. This keeps the dashboard counts accurate without requiring a manual refresh.

# 9. Notes System

## 9.1 Append-Only Design

Notes are append-only. They cannot be deleted or edited. Each note is stamped with author and timestamp at creation. Notes are stored in the task's notes field as an array of note objects.

## 9.2 Storage Format

notes: [

{ text: 'Note content', author: 'Team member', ts: 'ISO timestamp' },

...

]

Older data may have notes stored as a raw string. _notesArray(raw) normalises this to an array for display, ensuring backward compatibility.

## 9.3 Note Helpers

_notesArray(raw)              → always returns an array, handles string/array/null input

_addNote(pid, taskId, text, author)  → appends note to task and saves

_renderNotesList(elId, notes) → renders note list into the modal UI

# 10. WBS (Work Breakdown Structure)

## 10.1 Rendering Logic

renderWBS() groups all tasks for the current villa into a two-level tree:

- Outer group: by phaseId — Phase header row rendered for each phase

- Inner group: by subphaseId — Subphase header row rendered within each phase

- Task rows rendered as children of their subphase group

## 10.2 Collapse State

S.coll stores expand/collapse state. Keys:

ph_<phaseId>   → phase group collapsed if true

sp_<subphaseId> → subphase group collapsed if true

collapseAll() sets all ph_ and sp_ keys to true. expandAll() clears them. toggleSpC(spId) toggles a single subphase. togglePhC(phId) toggles a single phase.

## 10.3 Column Layout

| Column | Content |
| --- | --- |
| # | Row number |
| Task Name | Phase: phase name. Subphase: name + X/Y done count. Task: task name + priority/milestone badges |
| Assignee | Assigned team member |
| Dates | Planned start → end range |
| Dur | Duration in days |
| Progress | Phase/Subphase: duration-weighted %. Task: task's own progress % + mini bar |
| State | Status badge + cycle button |
| Actions | Edit and delete buttons |

# 11. Predecessor / Dependency Logic

Tasks can define predecessors stored as an array of {id, type} objects. Types are standard CPM link types:

| Type | Meaning |
| --- | --- |
| FS | Finish-to-Start (default): successor starts after predecessor finishes |
| SS | Start-to-Start: successor starts when predecessor starts |
| FF | Finish-to-Finish: successor finishes when predecessor finishes |
| SF | Start-to-Finish: successor finishes when predecessor starts |

⚠ Note Predecessor logic is stored but not actively enforced by the tool — there is no automated date-shifting or critical path computation. Predecessors are displayed as metadata for team reference.

# 12. Resource Management

Resources are stored in _cky_res as a map of id → resource object. Fields: id, name, role, email, phone, rate, avail (availability %), type, color.

Resources can be assigned to tasks via the assignee field. The Resource view shows all defined resources and their assignments across projects. There is no automated capacity calculation or conflict detection.

# 13. Baseline

A baseline is a point-in-time snapshot of all task planned dates and progress. It is stored in _cky_bl. Baseline data is used in the Baseline view to compare planned vs. actual schedule.

- setBaseline(): copies current task data (startDate, endDate, progress) into _cky_bl

- Baseline is not auto-updated — must be explicitly set by a team lead

- Once set, the baseline is frozen; task edits do not affect it

⚠ Note Currently only one baseline is stored at a time. There is no multi-baseline versioning. The 'Baseline Fixed: 32' dashboard card is hardcoded and does not reflect the stored baseline state.

# 14. Known Issues & Improvement Areas

## 14.1 Data Persistence

- RISK All data lives in localStorage — clearing browser data destroys all project state

- RISK No user authentication — any person on the same browser can modify any data

- RISK No multi-device sync — each browser has its own isolated data copy

## 14.2 Logic Inconsistencies

- ISSUE 'Baseline Fixed: 32' in the dashboard is hardcoded — not derived from data

- FIXED 'Total Villas: 95' was previously hardcoded — now uses villas.length dynamically

- FIXED 'In Progress' dashboard card was hardcoded at 2 — now dynamic (Active count)

- FIXED syncProjStatus previously only derived 3 statuses — now derives on-track and at-risk

- FIXED renderDetStats had an unused startedTs variable — removed

- FIXED renderGrid actStart fallback was using planned startDate instead of actualStartDate — fixed

- MINOR DB.save() double-call: syncProjStatus calls DB.save() and is itself called from saveTask() which also triggers a save — harmless but redundant

## 14.3 Backend Readiness

The following items are required for production deployment:

- REQUIRED Replace localStorage with a real database (PostgreSQL / Firebase / Supabase recommended)

- REQUIRED Add authentication and user sessions (team member login)

- REQUIRED Implement role-based permissions (viewer / editor / admin)

- REQUIRED Add real-time sync so multiple team members see each other's updates

- REQUIRED Add server-side backup and audit log

- REQUIRED Replace hardcoded 'Total Villas: 95' and 'Baseline Fixed: 32' with data-driven values

# 15. Function Quick Reference

| Function | Purpose |
| --- | --- |
| renderWBS() | Renders the full WBS table for the current villa |
| renderStats() | Renders dashboard stat cards and alert strip |
| renderGrid() | Renders the villa grid/cards on the dashboard |
| renderDetStats() | Renders detailed stats panel for the current villa (actuals, dates, progress) |
| syncProjStatus(pid) | Derives and saves villa status from task data |
| saveTask() | Saves Add/Edit task modal data to storage |
| openAddTask() | Opens task modal in Add mode (4 date fields) |
| openEditTask(id) | Opens task modal in Edit mode (Actual dates only) |
| cycSt(id) | Cycles a task through not-started → in-progress → completed |
| _wPct(tasks) | Returns duration-weighted progress % for a task array |
| _tmSetMode(mode) | Configures task modal UI for 'add' or 'edit' mode |
| _notesArray(raw) | Normalises notes field to always return an array |
| _addNote(pid, taskId, text, author) | Appends a note to a task |
| toggleSpC(spId, e) | Toggles subphase collapse in WBS |
| collapseAll() | Collapses all phases and subphases in WBS |
| DB.save() | Flushes all state to localStorage |
| gFilt(q, s) | Applies dashboard grid filters by query and status |
| showMain(view) | Switches the main content area to a named view |

Chanakya PM  |  System Logic Reference  |  Internal